TEHNICAL DATA SHEET

Local Action Groups documentation of institutional organization

1 Human Resources

At LAG level will perform the following activities:

a) information - communication;

b) call for projects;

c) support for  projects deponents;

d) organizing  process verification and decision on the submitted projects;

e) projects monitoring.

f) The Board of Appeals

For each LAG employee,  will prepare work documents, job description, in which will be included all activities to their participating and assignments  in these activities.

Human resources involved will respect the principle of equal opportunities and treatment both in relations with third persons involved in implementation and inside:

In relations with third parties shall refrain from any conduct that can be interpreted discriminatory;

Performance management strategies adopted will be based on reducing the ambiguity at  all levels and application of equal opportunities principle, basing on:

• Personal skills;

• Responsibilities;

• Information that the decision is based on the performance (promotion, remuneration);

• Values ​​promoted by the organization.

Work organization will be under Organization and Functioning International Regulation

a) information - communication;

Communication will be horizontally and vertically based on specific procedures for internal and external communication.

Information activities - communication within the Local Development Plan aimed at:

- Increasing public awareness of funding opportunities offered by LEADER axis through LAG Central Dobrogea;

- Increasing public awareness of the PLD and its objectives, priority axes and implementation mechanisms;

- Informing potential beneficiaries about: conditions of eligibility (potential beneficiaries, types of projects) to obtain funding under Local Development Plan; evaluation procedures of funding applications and provided term; selection criteria for operations to be financed; Local contacts that can provide information about the Local Development Plan;

- Increasing absorption ability by ensuring effective information on

projects funded through the Local Development Plan, the results obtained and models of best practices;

- ensuring access to information for all target groups;

- ensuring maximum transparency on information provided to general public about     allocation and management of funds under the Local Development Plan;

Dissemination of information must follow certain general principles, such as:

- accessibility, accuracy, objectivity, consistency and speed in delivering the message.

The messages to target groups should be written in an accessible way, using language that is easy to understand, avoiding technical terms and using concrete examples and successful projects, to provide a positive image to projects co-financed from EU funds. For successful information and communication measures in the Local Development Plan is essential a professional and stable cooperative relationship with the media representatives.

Officials from the administrative department for information-communication activities:

Administrative responsible, entertainer, accountant, secretariat responsible coordinator, technical responsible – engineer, financially responsible, external consultant.

b) call for projects;

Inside of LAG activities will be launched calls for proposals on various measures included in the Local Development Plan. For them, GAL will develop consistent procedures that ensure equality and the lack of any form of discrimination. Within this category of activities, the LAG staff will prepare a set of documents for each call for proposals, will initiate a public consultation process prior to officially launching of the call for proposals, will make the necessary amendments to the package of documents relating to the call then will make public the call for projects. GAL will realize for each of measures, a call for projects: For measures where are final beneficiaries that may be both individual and legal persons of private law and municipalities, will be organized calls for selection within each of beneficiary, public or private . The call will be approved by the Director Council. After approving the call for selection by the Director Council, within 15 days from the day following its adoption, it will be sent a copy of the approval to Ministry of Agriculture, and also will advertise the call in the territory through the media, flyers and posters in every community, part of the LAG.

Projects deponents will be supported by the consultants of the centers of consulting, management and specialized assistance in each village.

Responsible from the administrative department to support deponents

Administrative responsible- GAL coordinator - to oversee the activity

Animator - supporting and informing deponents in their territory

Secretariat responsible- administrative support for deponents

Technical responsible – for  project elaboration from technical point of view

Financially responsible - for project proper elaboration form financial point of view

project

Where appropriate, external consultant - support for all activities included in projects elaboration both for deponents and for administrative department personnel.

Projects submitted by final beneficiaries will respect the form and content conditions recommended, will be accompanied by the documents requested by the calling selection. The maximum term for submission of the projects will be specified in the guide and selection call. There can be projects deponents, beneficiaries as they were settled in this chapter Measure from this PLD, individual and legal persons of private law and local public institutions, which meet specific requirements for each of the presented. Also, LAG can be final beneficiary, when measures are of general interest, with reference to the strategic objectives of the program and when there are measures which have not been requested or received financial assistance in call selection and there is availabe credit

c) organizing verification and decision process on the submitted projects;

The verification and decision process on submitted projects will require an administrative conformity verification of applications files performed by LAG employees, a technical evaluation by the Technical Committee completed with a recommending report  by the selection committee (as the audit trail). After these stages, the project selection committee will determine the list of projects approved under procedures laid down in organization and operation regulation. Project Selection Committee will check the fulfillment of the conformity criteria stipulated in accordance with the call selection and present of all required documents. Also, the technical staff will realize the inspection of the place where the project will be carried out, for which aid is requested and shall issue a document which establishes that  works have not been started before signing the financing contract. After obtaining this document, Administrative responsible (Coordinator) will make a technical and economical report for each request in part in which will give a favorable or unfavorable opinion for requested grant funding. Applications that obtain favorable opinion will then be evaluated by LAG Selection Committee. It will prepare one document for each measure in which it shall record the scores obtained by the projects presented in descending order. The score of each project will be determined in accordance with the selection criteria established in the Local Development Plan. The outcome evaluation will be recorded in a reasoned report. In the base of the motivated report, prepared by the Selection Committee, the Direcor Council will issue, for each measure, a justified proposal that can be: - proposal to approve the request, specifying the amount and percentage of financing; - motivated proposal to reject funding due to lower score and inconsistency in the amount of that submission session open by LAG. After completion of the project selection in LAG, the  list of approved projects will be submitted to the Regional Center of Payments for Rural Development and Fisheries, together with a full report of that session, in order to sign contracts with the final beneficiaries of funding. The responsible of the administrative department for organizing the verification and decision process on the submitted projects:

Administrative responsible - coordinator - to oversee the work and present recommendation report  by the selection committee

Responsible Secretariat - administrative support for the registration projects stage at LAG

Technical responsible - for checking project compliance and project evaluation from

Technical point of view

Economic responsible- to verify project compliance and project evaluation from project financial point of view

External consultant - support for the project and to assess compliance check

technical and economic.

d). projects monitoring.

The monitoring of approved projects will be carried out by LAG employees and will follow the contractual terms assumed at the time of financing. Monitoring will act to ensure the implementation of projects under the established conditions, but will be able to provide an evolution image regarding the local development process in the territory.

Responsibles from the administrative department for monitoring projects:

Administrative responsible - coordinator - to oversee the work

Animator - to obtain information regarding the progress of projects in the territory, and for information on other projects undertaken in the territory for providing a global image of local territory development.

Secretariat responsible- administrative support for organizing field visits and realizing monitoring reports

Technical responsible - for monitoring visits effectuation

Economic responsible - for monitoring visits effectuation

External consultant - support for all activities in project monitoring both for beneficiaries and for administrative personnel department

e) The Appeals Committee

Inside LAG,  will operate a complaints committee consisting of 5 persons. From its component will not be part titular members and substitutes of committee selection described in item. 4 " Presentation of decision-maker partnership".

Procedure

LAG selection committee shall notify the applicant of selection result. Beneficiaries who have been notified by LAG that their projects were not be selected can submit complaints at LAG headquarters, within 5 days of  notification receipt. Complaints received will be reviewed by the Appeals Commission established on the LAG level, with a different composition from that of the Selection Committee. LAG will develop an Organizational and Operational Regulation for resolving complaints. After verifying complaints filed, the Appeals Commission will issue a complaints report containing the results of complaints analyze, report to be made public including by display. Result of appeal analysis  will be notified to the objector within 30 days of submitting the appeal. After the appearance of the report regarding solving the complaints on LAG site, the solution becomes final. Following settlement of disputes, LAG will publish the complaints report that will contain the name of the applicant and the projects that will be submitted to CDRJ / OJPDRP.