2 Tehnical Data Sheet consultations for elaborating PLD

Consultations for setting stages of  Local Development Plan elaboration:

a.  collection and centralization of information, building a local database with complete information.

All information collected nationwide were gathered in a database and used for the evaluation of economic, social, professional, cultural status of territory.

Work methodology:

b. Data collection: working groups were given 30 days to collect all the data in the field.

c. storage and interpretation of results, data were stored in a special file.

d. developing local SWOT analysis and diagnosis

e. Formulating vision of priorities and objectives.

Work schedule:

- Presentations in all partner communities for population information and consultation

- workshops, making diagnosis and SWOT analysis, drafting local development plan in consultation INSSE experts, environment, cadastre, historians, ethnographers, NGOs and external expert.

- Cooperation with the County Council, Prefecture, Department of Rural Development, OSPA, Agricultural  Consulting.

Expected results/ estimated

Professional performance.

Stable workforce in the area.

Employment through self-employment and employment.

Additional personal income.

Diversified and dynamised local economy.

The updated human resource structure.

Investments that ensure environmental protection.

Local economic growth

Restored and protected natural environment.

Standardised products.

VAB increased.

Meetings of working groups:

It organizes three special workshops for community members partners for Local Development Plan elaboration.

The first meeting aims at presenting data collected from the territory.

a. diagnosis presentation on themes.

b. Exchanges and share new ideas.

c. Search for more information.

To analyze the real economic situation of the territory RICA methodology is used by determining the number of UDE per farm

Meeting 2

a. establishing the main future actions.

b. formalization and structuring proposals.

c. organizing the meeting with AM for identifying the measures in PNDR adapted to proposed actions.

It is organized with the purpose of presenting SWOT analysis and diagnosis of the territory in its final form, the development vision of the territory as it was conceived by team work, present the priorities and objectives of future local development plan, ways of action and the implementation of measures in territory.

Must occur debate on SWOT analysis and prioritization of future development plan objectives, actions, projects and measures that will be implemented.

Meeting 3

a. Validation strategy

b. Presenting the conclusions, formalizing the partnership, establishing the selection committee.

c. Elaborate candidacy and re-discuss with AM.

d. Validation of the application file.

It shows the local development plan to be validated by the General Assembly.

Elaborate SWOT analysis and diagnosis

Following the actions taking place in the territory, analysis of data collected, interviews with community leaders or representatives of local institutions, working groups made SWOT analysis and diagnostic analysis. Items collected in the territory by the  3 work teams  will be assembled and thus formulate the elements of SWOT analysis and design "Local diagnostics", at this process participate animators from the territory.

Formulating objectives

Establishing measures to improve

Dissemination

- elaborating Dissemination and advertising materials:

It elaborates leaflets distributed in communities, during meetings, TV shows participation, etc.

It organize meetings in partener comunities for information and dissemination, it will be applied questionnaires regarding the development vision.

After consultations it validate the final version of formulating major strategic vision and objectives .