| 2 TEHNICAL DATA SHEET - Management Plan framework for LAG functioning |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Current No. | Activity | Who develop the activity |  | Responsible | Received document | Generated document | Who sign the document | Where is archived |  |
|  |  | Extern | Intern |  |  |  | Hierarchical position | Physical Archive-original | Copy |
| 1 | Convocation of LAG members meetings in order to establish the timetable for PLD assessing, monitoring and control |  | LAG | Secretary |  | Convening notice | LAG legal Responsible | LAG Secretariat | - |
| 2 | Organization of LAG partners meetings |  | LAG | LAG General Assembly |  | Minutes | Present members | LAG Secretariat | - |
| 3 | Approval of evaluation, control and monitoring ways regarding the Development Plan |  | LAG | LAG General Assembly |  | Minutes | Present members | LAG Secretariat | - |
| 4 | Gathering information for monitoring |  | LAG | Secretary and tehnical |  | Report | LAG legal Responsible | LAG Secretariat | - |
| 5 | Operative management and decisions taking |  | LAG | Tehnical and financial |  | Minutes+ decision | LAG legal Responsible | LAG Secretariat |  |
| 6 | Achievement of Local Development Plan’s intermediary evaluation throughout the implementation |  | LAG | Administrative responsible - Coordinator |  | Evaluation report | Administrative responsible - Coordinator | LAG Secretariat | Administrative |
| 7 | Presenting the evaluation reports to LAG Director Council |  | LAG | Administrative responsible - Coordinator |  | Minutes | Members of Director Council | LAG Secretariat | Administrative |
| 8 | Issuing proposals to improve the Local Development Plan by the Director Council |  | LAG | Director Council |  | Report with improvement proposals | Members of Director Council | LAG Secretariat | Administrative |
| 9 | Submits reports with improvement proposal to the LAG General Assembly to be studied |  | LAG | Secretary | Report with improvement proposals | Approve / Reject | Members of LAG General Assembly | LAG Secretariat |  |
| 10 | Implement improvement measures following their approval by the General Assembly |  | LAG | Administrative responsible - Coordinator |  | Report on the implementation of improvement measures | Administrative responsible –Coordinator | LAG Secretariat |  |
| 11 | Making quarterly progress reports to LAG Local Development Plan |  | LAG | Administrative Department |  | Progress Report | Administrative responsible -Coordinator | LAG Secretariat |  |
| 12 | Presentation of progress reports to LAG Director Council GAL |  | LAG | Administrative responsible - Coordinator | Quarterly Progress Report | Minutes | Members of Director Council | LAG Secretariat |  |
| 13 | Presentation of progress reports to General Assembly |  | LAG | Administrative responsible – Coordinator | Quarterly Progress Report | Minutes | Members of General Assembly | LAG Secretariat |  |
| 14 | Transmission of quarterly progress reports to the Ministry of Agriculture and Rural Development |  | LAG | Administrative responsible –Coordinator |  | Expression of interest | Administrative responsible -Coordinator | LAG Secretariat | - |
| 15 | Ensure publicity of results regarding quarterly monitoring in LAG territory via leaflets, brochures and website |  | LAG | Administrative Department | Monitoring report | Informative materials | Administrative responsible -Coordinator | LAG Secretariat | Administrative |
| 16 | Implementation of improvement measures following the analysis of the progress reports by the General Assembly and the approval of improvement measures |  | LAG | Administrative responsible –Coordinator |  | Report of implementation improvement measures | Administrative responsible -Coordinator | LAG Secretariat | Administrative |
| 17 | Monitoring Local Development Plan through the informatic system of the GAL |  | LAG | Administrative Department |  | Monitoring report | Administrative responsible -Coordinator | - | Administrative |
| 18 | Presentation of monitoring results to LAG Director Council |  | GAL | Secretary | Monitoring report | Minutes | Members of Direcor Council | LAG Secretariat | Administrative |
| 19 | Ensure publicity of results regarding computerizing monitoring in LAG territory via leaflets, brochures and website |  | LAG | Administrative Department | Control report | Informative materials | Administrative responsible -Coordinator | LAG Secretariat | Administrative |
| 20 | Controlling the implementation of the projects submitted in LAG throughout their implementation |  | LAG | Administrative Department |  | Control report | Administrative responsible - Coordinator | - | Administrative |
| 21 | Monitoring the compliance of project implementation graphics submitted on LAG |  | LAG | Administrative Department |  | Control report | Administrative responsible - Coordinator | - | Administrative |
| 22 | Ensuring the publicity of control results in the territory of LAG via leaflets, brochures and website |  | LAG | Administrative Department | Control report | Informative materials | Administrative responsible - Coordinator | LAG Secretariat | Administrative |
| 23 | Achievement of annual monitoring regarding the Local Development Plan |  | LAG | Administrative Department |  | Annual monitoring report | Administrative responsible - Coordinator | LAG Secretariat | Administrative |
| 24 | Presenting the annual monitoring report to LAG Director Council |  | LAG | Administrative responsible - Coordinator |  | Minutes | Members of Director Council | LAG Secretariat | Administrative |
| 25 | Issuing proposals to improve the Local Development Plan by the Director Council |  | LAG | Director Council |  | Report with improvement measures | Members of Director Council | LAG Secretariat | Administrative |
| 26 | Presentation of reports with improvement proposals to LAG General Assembly to be studied |  | LAG | Secretary | Report with improvement measures | Approve / Reject | Members of General Assembly | LAG Secretariat | Administrative |
| 26 | Transmission of the Annual Progress Report to the Ministry of Agriculture and Rural Development |  | LAG | Administrative responsible - Coordinator |  | Expression of interest | Administrative responsible - Coordinator | LAG Secretariat | - |
| 27 | Ensuring publicity of annual monitoring report results in LAG territory through leaflets, booklets and website |  | LAG | Administrative | Monitoring report | Informative materials | Administrative responsible - Coordinator | LAG Secretariat | Administrative |
| 28 | Implement improvement measures following their approval by the LAG General Assembly |  | LAG | Administrative responsible - Coordinator |  | Report regarding implementation of improvement measures | Administrative responsible - Coordinator | LAG Secretariat |  |
| 29 | Carrying out the ex-post evaluation of LAG Local Development Plan |  | LAG | Administrative |  | Ex-post monitoring report | Administrative responsible - Coordinator | LAG Secretariat | Administrative |
| 30 | Presentation of ex-post monitoring report to LAG Director Council |  | LAG | Administrative responsible - Coordinator |  | Minutes | Members of Director Council | LAG Secretariat | Administrative |
| 31 | Issuing improvement proposals of Local Development Plan by the Director Council |  | LAG | Director Council |  | Report with improvement proposals | Members of Director Council | LAG Secretariat | Administrative |
| 32 | Presentation of reports with improvement proposals to General Assembly to be studied |  | LAG | Secretary | Report with improvement proposals | Approve / Reject | Members of LAG General Assembly | LAG Secretariat | Administrative |
| 33 | Transmission of ex-post monitoring report to Ministry of Agriculture and Rural Development |  | LAG | Administrative responsible - Coordinator |  | Expression of interest | Administrative responsible - Coordinator | LAG Secretariat | - |
| 34 | Ensuring publicity of ex-post monitoring report results in LAG territory through leaflets, booklets and website |  | LAG | Administrative | Monitoring report | Informative materials | Administrative responsible - Coordinator | LAG Secretariat | Administrative |
| 35 | Implement improvement measures following their approval by the General Assembly of the GAL |  | LAG | Administrative responsible - Coordinator |  | Report regarding implementation of improvement measures | Administrative responsible - Coordinator | LAG Secretariat |  |

Correct administration of resources in the LAG is done by applying the Ordinance 34/2006 with subsequent amendments and speific legislation used to implement  projects in PNDR. LAG will use the following rules and administrative regulations.

| MANAGERIAL ACQUISITION AND PAYMENT PLAN |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Current No. | Activity | Who develop the activity |  | Responsible | Received document | Generated document | Who sign the document | Where is archived |  |
|  |  | Extern | Intern |  |  |  | Hierarchical position | Physical Archive-original | Copy |
| 1 | Issuing Decision regarding approval of tender documentation and naming evaluation offers committee for the award |  | LAG | Administrative Department |  | Decision regarding approval of tender documentation and naming evaluation offers committee for the award | Administrative responsible - Coordinator | LAG Secretariat | - |
| 2 | Issuing Explanatory note on the selection procedure for the award |  | LAG | Administrative Department |  | Explanatory note on the selection procedure for the award | Administrative responsible - Coordinator | LAG Secretariat | - |
| 3 | Elaboration Report of necessity and opportunity, estimating the value of public procurement contract |  | LAG | Administrative Department |  | Report of necessity and opportunity, estimating the value of public procurement contract | Administrative responsible - Coordinator | LAG Secretariat | - |
| 4 | Elaborating public procurement Calendar |  | LAG | Administrative Department |  | Public procurement Calendar | Administrative responsible - Coordinator | LAG Secretariat | - |
| 5 | Emitting explanatory note regarding the establishment of selection criteria |  | LAG | Administrative Department |  | Explanatory note regarding the establishment of minimum qualification requirements relating to economic, financial, technical and / or professional that must accomplished | Administrative responsible - Coordinator | LAG Secretariat | - |
| 6 | Elaboration of tender documentation |  | LAG | Administrative Department |  | The tender documentation for the application of award procedure | Administrative responsible - Coordinator | LAG Secretariat | - |
| 7 | Publication of notice for participation |  | LAG | Administrative Department |  | Notice for participation | Administrative responsible - Coordinator | LAG Secretariat | - |
| 8 | Expression of interest | Participating company |  |  | Expression of interest Technical and financial offer, accompanying documents |  | Participating company | LAG Secretariat | - |
| 9 | Declaration of confidentiality and impartiality |  | LAG | Administrative Department |  | Declaration of confidentiality and impartiality | Members of tender evaluation committee | LAG Secretariat | - |
| 10 | Carrying out the tender opening session and elaborating the minute |  | Evaluation committee | Commission President |  | Minutes of the tender opening session | Members of tender evaluation committee | LAG Secretariat | - |
| 11 | Requiring clarifications and additions documents |  | Commission President | Commission President |  | Address regarding request clarifications | Commission President | LAG Secretariat | - |
| 12 | Report procedure |  | Evaluation committee | Evaluation committee |  | Procedure report including centralized scores | Evaluation committee | LAG Secretariat | - |
| 13 | Communication of procedure result |  | Evaluation committee | Evaluation committee |  | Address regarding communication results | Evaluation committee | LAG Secretariat | - |
| 14 | Signing the service contract | Winning company | Administrative Department | Administrative Department |  | Contract | Administrative responsible - Coordinator |  | - |
| 15 | Award notice |  | Administrative Department | Administrative Department |  | Award notice contract | Administrative responsible - Coordinator | LAG Secretariat | - |
| 16 | Additional Act |  | Administrative Department | Administrative Department |  | Additional Act | Administrative responsible - Coordinator | LAG Secretariat | - |
| 17 | Acceptance report | Winning company | LAG | Administrative Department |  | Acceptance report | Administrative responsible - Coordinator | LAG Secretariat | - |
| 18 | Fiscal invoice | Winning company |  |  | Fiscal invoice |  | Administrative Department | Financial department | Administrative Department |
| 19 | Emitting explanatory note |  | Administrative Department | Project Manager |  | Explanatory note for CFP exercise | Project Manager | Financial department | LAG Secretariat |
| 20 | Emitting employment proposal |  | Administrative Department | Project Manager |  | Proposal for expense engagement | Administrative responsible - Coordinator | Financial department | LAG Secretariat |
| 21 | Emitting budgetary expense engagement |  | Administrative Department | Financially responsible |  | Budgetary expense engagement | Administrative responsible - Coordinator | Financial department | LAG Secretariat |
| 22 | Emitting approving invoices for payment |  | Administrative Department | Financially responsible |  | Approving invoices for payment | Administrative responsible - Coordinator | Financial department | LAG Secretariat |
| 23 | Emitting payment order |  | Administrative Department | Financially responsible |  | Payment order | Administrative responsible - Coordinator | Financial department | LAG Secretariat |
| 24 | Emitting address to Treasury |  | Administrative Department | Financially responsible |  | Address to Treasury requesting to make payments | Administrative responsible - Coordinator | Financial department | LAG Secretariat |
| 25 | Statement | Treasury |  |  | Statement |  | Treasury | Financial department | LAG Secretariat |