7  Specific Curriculum reference to the modality of elaborating guidelines for calls launching

: Worksheet on the selection of the investment project

If the selected project is an investment project will be carried out these various activities by CRPDRP:

- verifying the eligibility of the projects and conducting field verification of the potential beneficiary by APDRP territorial structures;

- transmission of the notification by CRPDRP to the beneficiary and LAG on approving or not approving the project;

- signing the contract between the beneficiary and the Regional Center of Payments for Rural Development and Fishing (CRPDRP) if the project was approved;

The way of responsibilities distribution between LAG Agency for Payments and Managing Authority for each stage of a dossier circuit.

| Task | LAG | CDRJ AM | Agency for Payments |
| --- | --- | --- | --- |
| Information | X |  |  |
| Support for projects elaboration | X |  |  |
| Launching the call for projects | X |  |  |
| Selection of projects | X |  |  |
| Administrative control of files |  | X | X |

Worksheet on selecting service projects

If it is a service project then will be followed the next steps:

- CRPDRP verifies the eligibility of projects and transmits a notification to the beneficiary and the LAG,  of announcement regarding the project approval or disapproval

- signing a contract between the beneficiary and CRPDRP;

Funding beneficiaries are required to start implementing the project in the period specified in the funding contract. Starting project execution will be communicated through a standard document provided by the LAG. After notification of project  commencement implementation, GAL technical staff can make "territorial" visits  to meet the conditions assumed by the financing contract.

Not starting the project implementation in the specified period from the contract of finance leads to loss aid granted to the final beneficiary.

Completion of works / activities needed to implement the project will be carried out within the period specified in the funding contract. The deadline for completion of the project implementation may be extended at the request of the financing  beneficiary, for a time period which may not exceed half the initial fixed term. The request to extend the deadline for project implementation, in which will present the reason, will be analyzed by LAG administrative responsible (coordinator), which depending on the nature of the investment that is done, the deadline set in the contract, level of implementation thereof, cause of extension and any other external issues, will realized a report that will be presented to the Director Council, which can approve or reject the request.

If after analysis, the LAG Director Council decides to grant the extension term of the project implementation, this decision will be communicated to the Regional Centre of Payments for Rural Development and Fisheries in order to analyze the possibility of concluding an addendum to the initial financing contract.

During the execution of a project, the beneficiary of financial assistance may submit in written proposals for amending the project. The request will be considered by the LAG Administrative responsible (Coordinator) which will issue a favorable or unfavorable report of proposed changes. The report may be favorable only if the change does not lead to an increase of the initial value of the project assumed under the contract, to a change of objectives or distortion of competition in the market. The report will be presented to the Director Council that will solve the problem of admission or non-admission changes. If the requested amendments also need modification of the financing contract, then the report will be submitted for approval to LAG General Assembly.

The result will be communicated to the Regional Centre of Payments for Rural Development and Fisheries.

Programming visits (checks) will have to take into account certain principles, such as: the effectiveness of such actions, keeping good contractual relations, verification only of technical issues related to the project etc.

Through control will be follow the use of information derived from the monitoring project  activity as a basis for further decisions, stopping or improvement project.

Issues considered include: trends in obtained results, results to feedback procedures, external changes, correct deviations detected or predicted, the partial results obtained. To ensure effective supervision of a project will put in place a feedback mechanism to correct deviations in time. If possible deviations were anticipated in the planning phase, than it is possible to apply corrective actions or deviations appearance can be impeded by appropriate preventive actions. The project control will follow only successful implementation of the project, not finding the culprits or their punishment.

The way of responsibilities distribution between LAG Agency for Payments and Managing Authority for each stage of a dossier circuit

| Task | LAG | CDRJ AM | Agency for Payments |
| --- | --- | --- | --- |
| Information | X |  |  |
| Support for projects elaboration | X |  |  |
| Launching the call for projects | X |  |  |
| Selection of projects | X |  |  |
| Administrative control of files |  | X | X |

Project of a unit of study

• The unit of study LAG guidelines elaboration.

| Content | Specific skills | Learning activities | Resources | Evaluation |
| --- | --- | --- | --- | --- |
| General provisions Presentation of the Measure implementing development strategies Accessing grants allocated for Measure The procedure for selection of projects under the Local Action Group Conformity and eligibility at APDRP level Selection Eligible and ineligible expenses within the project. Maximum value of grants (aid intensity). State aids. Payments in advance. The documents required for the application form | C1 identifying general provisions stipulated in the development strategy C2 identifying amounts from LAG strategy C3 elaborating selection criteria according to strategy C4 elaborating conformity file C5 making the selection procedure 6 verification of eligible ineligible expenditure, aid intensity, prepayment conditions C7 Verification of annexed needed documents | Exercises on introduction in form of general provisions and presenting measure Exemplification and exercises on the steps and conditions of access Exercises on making the selection procedure Exercise regarding conformity file elaborating Exercises on identifying the elements of selection procedure from the strategy Exercises on different measures, according to the LAG strategy Exercise on checking the list annexed documents | Exposure, exercise, auxiliary for 1hour Conversation, case study, exercise auxiliary For 1 hour Exercise, questioning, Auxiliary, the documentary file . For 1hour Conversation, self study based mat. Auxiliary Time 2:00 h Conversation, exercise, documentary file Time 1 h Conversation, self study auxiliary materials Case Study additional curriculum | Systematic observation Formative evaluation Observation file Systematic observation Systematic observation Systematic observation Systematic observation Portfolio |