Tehnical Data Sheets 1 The establishment of internal monitoring and evaluation criteria

LAG is responsible for managing and implementing the Local Development Plan effectively in relation to its objectives and in accordance with Article 75 of Council Regulation (EC) nr.1698 / 2005.

The device monitoring, evaluation and control implemented by the LAG includes:

• Taking operational decisions on the implementation (or trouble-shooting);

• Perform daily LAG management;

• Timely and proper execution of the management resources procedures;

• Facilitate coordination between activities of LAG departments;

• Monitoring and timely reporting on the achievements and results of implementing LAG Local Development Plan;

• Communication status of development strategy implementation as LAG decision makers, namely the General Assembly and Directors Council;

Monitoring

Monitoring confer the possibility of periodic review, adaptation action plan, update initially set deadlines atualizarea and anticipate potential risks.

Monitoring provides such a rigorous and transparent device of viewing the way how occurs the financial management of development strategy implementation that allows the systematic collection and structuring of data on developed activities.

Monitoring instruments used in the implementation of the strategy:

Monitoring calendar:

Determining deadlines for implementing the measures,

Develop monitoring reports;

Regular reports:

Preparing reports to determine the stage in which is the process of implementing the strategy;

Transversal meetings

The methodology used for LAG operative adaptation of decisions regarding implementation.

IT monitoring of the LAG Local Development Plan will materialize by storing statistical information on the degree of implementation in a monitoring software which will allow  rapid evaluation and monitoring of the degree of implementation and fulfillment of objectives at any time. So, it will be analyzed comparative the proposed indicators and results achieved through the implementation of projects in the LAG.

To carry out the daily management of the project will be collected field data from beneficiaries, animators, technical sector, financial department, etc. - data collection are the responsibility of the Secretariat .

This allows operative decision making on project implementation, identify the problems and solve them and correct operative management of resources.

Quarterly report on the implementation of Local Development Plan. Monitoring should provide data on the state of achievement of plan objectives and strategy implementation in relation to the outcome indicators established.

Monitoring the implementation of the Local Development Plan envisages:

- Periodic evaluation of progress made towards achieving the specific objectives of the Plan

- Examining the implementing results of each measure and monitoring the quality of implementing financed projects;

- Examining the obtained results;

- Develop recommendations and proposals to improve the impact of the plan;

In meetings which aimed analysis of annual and quarterly progress reports, the Director Council and the General Assembly must:

-  to carry out periodic evaluation of registered progress towards reaching specific goals of the Local Development Plan;

- to examine both the implementation results of each measure, and quality of Local  Development Plan implementation;

- to analyze and approve the annual progress report and / or quarterly evaluation reports, before being sent to the Ministry of Agriculture and Rural Development;

- to elaborate recommendations and proposals to improve the impact of the strategy

In order to emphasize the degree of Plan implementation, LAG will prepare an Annual Progress Report which will contain all information on the progress in implementing the plan.

The annual progress report includes the following elements:

- Tables on financial implementation plan for each measure;

- Monitoring tables which include quantitative information on the basis of output and result set for each measure in the strategy;

- Analysis of the result of plan  monitoring.

Reports will be submitted for approval by the Director Council and the General Assembly and will be sent to the Ministry of Agriculture and Rural Development.

In meetings aimed as analysis of annual and quarterly progress reports, the Director Council and the General Assembly must:

- carry out regular assessments of progress towards specific objectives of the Local Development Plan;

- Both to examine the results of implementation of each measure, and quality of implementation of the development plan;

-  to carry out periodic evaluation of registered progress towards reaching specific goals of the Local Development Plan;

- to examine both the implementation results of each measure, and quality of Local  Development Plan implementation